## WBS Dictionary
Code | Nodes (Events) | Project, Task, Work Package (Activity) | Description | Critical Path | People | T (Opt) | T (ML) | T (Pess) | T Exp | σ | σ ^2 | Start Date | End Date | Duration in | Comments
1.0 | Planning | [13 empty] | Planning phase
1.1 | Planning | Define project scope | Defining the scope of the project, including objectives and deliverables. |  | Kseniia Piskun | 1 | 2 | 3 | 2 | 0.33333 | 0.11111 | 02/15/2025 | 02/16/2025 | 1 | Scope definition
1.2 | Planning | Identify stakeholders | Identifying all the stakeholders involved in the project, including team members and clients. |  | Kseniia Piskun | 1 | 1.5 | 2 | 1.5 | 0.16667 | 0.027778 | 02/16/2025 | 02/17/2025 | 1 | Stakeholder mapping
1.3 | Planning | Set timeline and budget | Creating a timeline and budget plan for the entire project. |  | Kseniia Piskun | 2 | 3 | 4 | 3 | 0.33333 | 0.11111 | 02/17/2025 | 02/19/2025 | 3 | Setting the schedule and budget
1.4 | Planning | Set up team roles and responsibilities | Assigning roles and responsibilities to the project team. |  | Kseniia Piskun | 1 | 1.5 | 2 | 1.5 | 0.16667 | 0.027778 | 02/19/2025 | 02/20/2025 | 2 | Assigning roles
2.0 | Design & Development | [13 empty] | Design and development phase
2.1 | Design & Development | UI/UX Design | Designing the user interface and user experience. | [11 empty] | UI design
2.1.1 | Design & Development | Design app wireframes | Creating wireframes for the app design. |  | Alice | 2 | 3 | 4 | 3 | 0.33333 | 0.11111 | 02/21/2025 | 02/23/2025 | 3 | Wireframe creation
2.1.2 | Design & Development | Develop interactive prototypes | Developing interactive prototypes for testing. |  | Alice | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 02/23/2025 | 02/27/2025 | 5 | Prototype development
2.1.3 | Design & Development | UI/UX design approval | Getting approval for the UI/UX designs from stakeholders. |  | Alice | 2 | 3 | 4 | 3 | 0.33333 | 0.11111 | 02/27/2025 | 02/28/2025 | 2 | Approval process
2.2 | Design & Development | Machine Learning Development | Develop machine learning models for gesture recognition. | [11 empty] | ML model development
2.2.1 | Design & Development | Collect training data for gestures | Gathering gesture data for training machine learning models. |  | Alice B. | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 02/22/2025 | 02/25/2025 | 4 | Data collection
2.2.2 | Design & Development | Train machine learning models | Training machine learning models to recognize gestures. |  | Alice B. | 4 | 5 | 6 | 5 | 0.33333 | 0.11111 | 02/26/2025 | 03/02/2025 | 5 | Training models
2.2.3 | Design & Development | Test gesture recognition accuracy | Evaluating the accuracy of the gesture recognition models. |  | Alice B. | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 03/03/2025 | 03/05/2025 | 3 | Model testing
2.3 | Design & Development | Backend Development | Developing the backend for cloud integration and SmartHome device control. | [11 empty] | Backend integration
2.3.1 | Design & Development | Set up database and cloud infrastructure | Setting up the cloud infrastructure for data storage and user settings synchronization. |  | Alice C. | 5 | 6 | 7 | 6 | 0.33333 | 0.11111 | 02/20/2025 | 02/25/2025 | 6 | Infrastructure setup
2.3.2 | Design & Development | Develop API for device control | Developing an API to control SmartHome devices. |  | Alice C. | 4 | 5 | 6 | 5 | 0.33333 | 0.11111 | 02/26/2025 | 03/03/2025 | 6 | API development
2.3.3 | Design & Development | Backend integration with SmartHome devices | Integrating the backend with the SmartHome devices. |  | Alice | 5 | 6 | 7 | 6 | 0.33333 | 0.11111 | 03/04/2025 | 03/07/2025 | 4 | Device integration
2.4 | Design & Development | Mobile Development | Developing the mobile app for iOS, integrating gesture control and backend services. |  | Alice D. | [9 empty] | Mobile app development
2.4.1 | Design & Development | Implement gesture recognition API | Implementing gesture recognition functionality for mobile. |  | Alice D. | 4 | 5 | 6 | 5 | 0.33333 | 0.11111 | 03/02/2025 | 03/05/2025 | 4 | API integration
2.4.2 | Design & Development | Integrate backend API with mobile app | Integrating backend API with the mobile app to enable device control. |  | Alice D. | 5 | 6 | 7 | 6 | 0.33333 | 0.11111 | 03/06/2025 | 03/10/2025 | 5 | Mobile app integration
2.4.3 | Design & Development | Mobile app development for iOS | Developing the core iOS app for the gesture-based control. |  | Alice D. | 5 | 7 | 9 | 7 | 0.66667 | 0.44444 | 03/11/2025 | 03/20/2025 | 10 | App development
2.4.4 | Design & Development | Mobile app testing | Testing the iOS app across different devices. |  | Alice D. | 4 | 5 | 6 | 5 | 0.33333 | 0.11111 | 03/21/2025 | 03/25/2025 | 5 | Testing
3.0 | Testing & Deployment | [13 empty] | Testing and deployment phase
3.1 | Testing & Deployment | Unit Testing | Test all components of the application to ensure they function as expected. |  | Brandon | [9 empty] | Unit testing
3.1.1 | Testing & Deployment | Test mobile app components | Test individual components of the mobile app. |  | Brandon | 2 | 3 | 4 | 3 | 0.33333 | 0.11111 | 03/26/2025 | 03/27/2025 | 2 | Component testing
3.1.2 | Testing & Deployment | Test backend services | Test the backend services for stability. |  | Brandon | 2 | 3 | 4 | 3 | 0.33333 | 0.11111 | 03/28/2025 | 03/29/2025 | 2 | Backend testing
3.2 | Testing & Deployment | User Testing | Test with real users to assess the usability and gesture recognition accuracy. |  | Brandon B. | [9 empty] | User testing
3.2.1 | Testing & Deployment | Test gesture recognition | Test gesture recognition with real-world input. | Yes | Brandon B. | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 03/30/2025 | 04/01/2025 | 3 | Recognition testing
3.2.2 | Testing & Deployment | Test SmartHome device integration | Test the integration with SmartHome devices. | Yes | Brandon B. | 3 | 4 | 5 | 4 | 0.33333 | 0.11111 | 04/02/2025 | 04/04/2025 | 3 | Device integration testing
3.2.3 | Testing & Deployment | Get user feedback | Get feedback from users after testing. | Yes | Brandon B. | 2 | 3 | 4 | 3 | 0.33333 | 0.11111 | 04/05/2025 | 04/06/2025 | 2 | Feedback collection
3.3 | Testing & Deployment | App Deployment | Deploy the app to the App Store and monitor performance. |  | Brandon C. | [9 empty] | App deployment
3.3.1 | Testing & Deployment | Deploy app to App Store | Deploy the app to the App Store. | Yes | Brandon C. | 1 | 2 | 3 | 2 | 0.33333 | 0.11111 | 04/07/2025 | 04/08/2025 | 2 | App store submission
3.3.2 | Testing & Deployment | Post-launch monitoring | Monitor app performance after launch. |  | Brandon C. | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | 04/09/2025 | Ongoing | Ongoing | Post-launch monitoring
4.0 | Post-Deployment | [13 empty] | Post-deployment phase
4.1 | Post-Deployment | Monitor app usage | Monitor how the app is used after deployment. |  | Claire | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | 04/09/2025 | Ongoing | Ongoing | Usage monitoring
4.2 | Post-Deployment | Collect user feedback for improvements | Collect feedback for improvements in future updates. |  | Claire | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | 04/09/2025 | Ongoing | Ongoing | Feedback gathering
4.3 | Post-Deployment | Bug fixes and updates | Fix any bugs and provide updates. |  | Claire | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | 04/10/2025 | Ongoing | Ongoing | Bug fixing
| Total |  |  |  |  | 67 | 90 | 113 | 90 | 7.6667 | 58.7778 |  |  | 83
Durations:
Planned Total Project Duration: |  | 83
Optimistic Time (T Opt): |  | 67
Most Likely Time (T ML): |  | 90
Pessimistic Time (T Pess): |  | 113
Time to Complete Job with Confidence:
95% Confidence Time: |  | 105.0267
Z | 1.96
99% Confidence Time: |  | 109.78
Z | 2.58

## Scope Control
Item # | WBS Code | DOR (Description of Requirement) | Description | Units of Measure | Units of Measure Planned | Date Started | Date Ended | Units of Measure Achieved | Comment
1 | 1.1 | Define Project Scope | Defining the scope of the project, including objectives and deliverables. | 100% (Completion) | 100% | 02/15/2025 | 02/16/2025 | 100% (Scope defined) | Scope definition
2 | 1.2 | Identify Stakeholders | Identifying all the stakeholders involved in the project. | 100% (Completion) | 100% | 02/16/2025 | 02/17/2025 | 100% (Stakeholders identified) | Stakeholder mapping
3 | 2.1.1 | Design App Wireframes | Creating wireframes for the app design. | 100% (Completion) | 100% | 02/21/2025 | 02/23/2025 | 100% (Wireframes designed) | Wireframe creation
4 | 2.2.1 | Collect Training Data for Gestures | Gathering gesture data for training machine learning models. | Number of gestures collected | 3000 | 02/22/2025 | 02/25/2025 | 3000 gestures | Data collection
5 | 2.3.1 | Set Up Database and Cloud Infrastructure | Setting up the cloud infrastructure for data storage and user settings synchronization. | 100% (Completion) | 100% | 02/20/2025 | 02/25/2025 | 100% (Infrastructure set up) | Infrastructure setup
6 | 2.4.1 | Implement Gesture Recognition API | Developing API to enable gesture recognition functionality. | 100% (Completion) | 100% | 2025-02-03 | 2025-05-03 | 100% (API integrated) | API integration
7 | 3.1.1 | Test Mobile App Components | Testing mobile app components for functionality. | % of app components tested | 100% | 03/26/2025 | 03/27/2025 | 70%(ongoing) | Component testing
8 | 3.3.1 | Deploy App to App Store | Deploying the app to the App Store for release. | 100% (Completion) | 100% | 2025-07-04 | 2025-08-04 | 0%(App not finished) | App submission
9 | 4.1 | Monitor App Usage | Monitoring how users interact with the app after launch. | % of active users tracked |  | 2025-09-04 | Ongoing | 0% (Ongoing monitoring) | Usage monitoring
10 | 4.2 | Collect User Feedback for Improvements | Collecting feedback from users for future improvements. | % of users providing feedback |  | 2025-09-04 | Ongoing | 0% (Ongoing feedback collection) | Feedback gathering

## Cost Control
Item # | WBS Code | Description | Planned Cost $ | Actual Cost $ | Cost Variance $ | Cumulative Planned Cost $ | Cumulative Actual Cost $ | Cost Performance Index (CPI) | Comment
1 | 1.1 | Define Project Scope | 500 | 480 | 20 | 500 | 480 | 1.0417 | Cost for project planning phase
2 | 1.2 | Identify Stakeholders | 300 | 350 | -50 | 800 | 830 | 0.96386 | Additional stakeholder meetings
3 | 2.1.1 | Design App Wireframes | 1000 | 1100 | -100 | 1800 | 1930 | 0.93264 | Additional design revisions
4 | 2.2.1 | Collect Training Data for Gestures | 600 | 650 | -50 | 2400 | 2580 | 0.93023 | Increased data collection efforts
5 | 2.3.1 | Set Up Database and Cloud Infrastructure | 1500 | 1200 | 300 | 3900 | 3780 | 1.0317 | Under budget for infrastructure setup
6 | 2.4.1 | Implement Gesture Recognition API | 800 | 850 | -50 | 4700 | 4630 | 1.0151 | Slightly over budget due to API complexity
7 | 3.1.1 | Test Mobile App Components | 700 | 750 | -50 | 5400 | 5380 | 1.0037 | Minor overrun due to additional testing
8 | 3.3.1 | Deploy App to App Store | 200 | 250 | -50 | 5600 | 5630 | 0.99467 | App store submission fees higher than expected
9 | 4.1 | Monitor App Usage | 100 | 100 | 0 | 5700 | 5730 | 0.99476 | On-budget monitoring
10 | 4.2 | Collect User Feedback for Improvements | 200 | 180 | 20 | 5900 | 5910 | 0.99831 | Slight savings due to online feedback tools
Total | [5 empty] | 36700 | 36880

## Schedule control
Item # | WBS Code | Description | Plannedtart Date | Planned End Date | Actualtart Date | Actual End Date | Schedule Variance (SV) | Cumulative Planned Duration(s) | Cumulative Actual Duration(s) | Percent Complete | Schedule Performance Index (SPI) | Comment
1 | 1.1 | Define Projectcope | 02/15/2025 | 02/16/2025 | 02/15/2025 | 02/16/2025 | 0 | 1 | 1 | 100% | 1 | On time, no delays
2 | 1.2 | Identifytakeholders | 02/16/2025 | 02/17/2025 | 02/16/2025 | 02/17/2025 | 0 | 1 | 1 | 100% | 1 | No delays, finished on time
3 | 2.1.1 | Design App Wireframes | 02/21/2025 | 02/23/2025 | 02/21/2025 | 02/23/2025 | 0 | 3 | 3 | 100% | 1 | Task completed on time
4 | 2.2.1 | Collect Training Data for Gestures | 02/22/2025 | 02/25/2025 | 02/22/2025 | 02/26/2025 | 0 | 4 | 4 | 100% | 1 | Task delayed by 1 due to data collection challenges
5 | 2.3.1 | Set Up Database and Cloud Infrastructure | 02/20/2025 | 02/25/2025 | 02/20/2025 | 02/24/2025 | -1 | 6 | 5 | 100% | 1.2 | Finished 1 ahead ofchedule
6 | 2.4.1 | Implement Gesture Recognition API | 2025-02-03 | 2025-05-03 | 2025-02-03 | 2025-06-03 | 1 | 4 | 5 | 80% | 0.8 | Task delayed by 1 due to integration issues
7 | 3.1.1 | Test Mobile App Components | 03/26/2025 | 03/27/2025 | 03/26/2025 | 03/29/2025 | 1 | 2 | 3 | 67% | 0.66667 | Testing ran over time, added extra for bug fixes
8 | 3.3.1 | Deploy App to Apptore | 2025-07-04 | 2025-08-04 | 2025-07-04 | 2025-09-04 | 1 | 2 | 3 | 0% | 0.66667 | Slight delay inubmission due to app finalization
9 | 4.1 | Monitor App Usage | 2025-09-04 | Ongoing | 2025-09-04 | Ongoing |  | Ongoing | Ongoing | 100% | N/A | Continuous monitoring phase
10 | 4.2 | Collect User Feedback for Improvements | 2025-09-04 | Ongoing | 2025-09-04 | Ongoing |  | Ongoing | Ongoing | 100% | N/A | Feedback collection ongoing

## Periodic meeting agenda
Meeting # | Date | Time | Location | Participants | Agenda Items | Duration | Action Items | Responsible Person | Status
1 | 02/20/2025 | 10:00 | Conference Room 1 | Kseniia Piskun, Alice B., Alice C., Brandon B. | - Define project scope | 1 hour | Scope finalized | Kseniia Piskun | Completed
2 | 02/22/2025 | 11:00 | Conference Room 2 | Kseniia Piskun, Alice B., Alice C. | - Design app wireframes | 1 hour | Design finalized | Alice B. | Completed
3 | 02/25/2025 | 9:00 | Virtual | Kseniia Piskun, Alice D., Brandon C. | - Review gesture recognition API progress | 1.5 hours | Continue testing | Alice D. | Completed
4 | 02/27/2025 | 10:30 | Conference Room 1 | Kseniia Piskun, Alice C., Alice B., Brandon B. | - Finalize UI/UX designs | 1 hour | Approval pending | Alice B. | In Progress
5 | 2025-01-03 | 9:30 | Virtual | Kseniia Piskun, Alice B., Brandon C. | - Test SmartHome device integration | 1 hour | Integration complete | Brandon C. | Not Started
6 | 2025-03-03 | 11:00 | Conference Room 2 | Kseniia Piskun, Alice D., Brandon B. | - Review app deployment progress | 1.5 hours | Deployment pending | Brandon B. | Not Started
7 | 2025-06-03 | 9:00 | Conference Room 1 | Kseniia Piskun, Alice C., Alice D. | - Discuss user feedback | 1 hour | Feedback gathered | Alice D. | Not Started
8 | 2025-09-03 | 10:30 | Virtual | Kseniia Piskun, Brandon C., Alice B. | - Post-launch monitoring plan | 1 hour | Monitoring setup | Brandon C. | Not Started
9 | 2025-12-03 | 14:00 | Conference Room 1 | Kseniia Piskun, Claire, Alice D. | - Discuss bug fixes and updates | 1 hour | Issue resolution ongoing | Claire | Not Started

## Periodic meeting schedule
Meeting # | Date | Time | Location | Expected Attendance | Purpose | Duration | Frequency
1 | 02/20/2025 | 10:00 | Conference Room 1 | Kseniia Piskun, Alice B., Alice C., Brandon B. | Kickoff meeting, define scope, and assign roles | 1 hour | Once (project start)
2 | 02/22/2025 | 11:00 | Conference Room 2 | Kseniia Piskun, Alice B., Alice C. | Finalize wireframes and discuss UI design | 1 hour | Once
3 | 02/25/2025 | 9:00 | Virtual | Kseniia Piskun, Alice D., Brandon C. | Discuss API progress and identify potential issues | 1.5 hours | Once (project stage transition)
4 | 02/27/2025 | 10:30 | Conference Room 1 | Kseniia Piskun, Alice B., Alice C., Brandon B. | Approve UI/UX designs and discuss next steps | 1 hour | Once
5 | 2025-01-03 | 9:30 | Virtual | Kseniia Piskun, Alice B., Brandon C. | Review gesture recognition API integration | 1 hour | Once
6 | 2025-03-03 | 11:00 | Conference Room 2 | Kseniia Piskun, Alice D., Brandon B. | Review testing and integrate feedback | 1.5 hours | Once (project stage transition)
7 | 2025-06-03 | 9:00 | Conference Room 1 | Kseniia Piskun, Alice C., Alice D. | Discuss feedback and changes from testing phase | 1 hour | Once
8 | 2025-09-03 | 10:30 | Virtual | Kseniia Piskun, Brandon C., Alice B. | Monitor app performance post-launch | 1 hour | Once (post-launch)
9 | 2025-12-03 | 14:00 | Conference Room 1 | Kseniia Piskun, Claire, Alice D. | Plan for bug fixes and future updates | 1 hour | Once

## Action item list
Action Item # | Action Item Description | Responsible | Due Date | Priority | Status | Comments
1 | Define project scope | Kseniia Piskun | 02/16/2025 | High | Completed | Initial scope defined
2 | Identify key stakeholders | Kseniia Piskun | 02/17/2025 | High | Completed | All team members identified
3 | Design wireframes for UI | Alice B. | 02/23/2025 | High | In Progress | Awaiting feedback from Kseniia
4 | Develop interactive prototypes | Alice B. | 02/27/2025 | Medium | Pending | Will begin after wireframes are finalized
5 | Collect training data for gestures | Alice B. | 02/25/2025 | High | Pending | Data collection from sensors
6 | Develop backend API for device control | Alice C. | 2025-03-03 | High | Pending | API setup for SmartHome device integration
7 | Integrate backend API with mobile app | Alice D. | 2025-10-03 | High | Pending | Integrating API with mobile app to control devices
8 | Test gesture recognition accuracy | Brandon B. | 2025-05-03 | High | Pending | Testing on multiple devices
9 | Deploy app to App Store | Brandon C. | 2025-08-04 | High | Pending | Waiting for final approval
10 | Post-launch monitoring | Claire | 2025-09-04 | High | Ongoing | Monitoring app performance and usage
11 | Collect feedback from users | Claire | 2025-10-04 | Medium | Ongoing | Feedback collection from early users
12 | Bug fixes and updates | Claire | Ongoing | High | Ongoing | Regular updates post-launch

## Change control form
Change Control Item # | Change Request Description | Requested By | Date Requested | Impact on Scope | Impact on Schedule | Impact on Cost | Reason for Change | Approving Authority | Approval Date | Implementation Plan | Comments
1 | Modify gesture recognition training dataset to include additional gestures | Alice B. | 02/18/2025 | Increase in scope to include new gesture categories | 3 additional days for training model | $2,000 for additional data collection and processing | To improve the model accuracy | Kseniia Piskun | 02/19/2025 | Dataset update followed by training session extension | Necessary to increase app accuracy
2 | Extend backend server infrastructure due to increased load | Alice C. | 2025-02-03 | Expanded to include more server instances | 2 additional weeks for implementation | $5,000 for extra infrastructure costs | Increased user base expected | Brandon C. | 2025-03-03 | Provision of new servers and scaling backend | Critical for system reliability
3 | Modify mobile app UI for better accessibility (new font sizes and colors) | Alice D. | 2025-10-03 | Minor scope change for accessibility improvements | No additional time required | $1,500 for UI redesign and testing | To comply with accessibility guidelines | Claire | 2025-11-03 | Design changes followed by user testing | Important for inclusivity
4 | Delay app launch due to delay in testing phase | Brandon B. | 03/25/2025 | No change in scope | 5 additional days for testing | No cost change | Testing delays identified during integration | Kseniia Piskun | 03/26/2025 | Rescheduling of app launch to ensure stable version | To ensure app reliability post-launch
5 | Change the feedback collection method from in-app to email surveys | Claire | 2025-05-04 | Change in scope for feedback method | 1 extra day to update app for new feedback method | $500 for app update and email system setup | To streamline feedback collection | Brandon C. | 2025-06-04 | Update app to integrate email feedback feature | Helps in collecting more diverse feedback
6 | Add new feature for smart device control from mobile app | Alice D. | 2025-12-03 | New feature for controlling additional devices | 7 days required for feature development | $3,000 for device integration | Client request for additional device support | Claire | 03/14/2025 | Develop new feature and integrate with mobile app | Significant feature improvement requested by clients

## Risk log
Risk ID | Risk Description | Likelihood | Impact | Priority | Mitigation Strategy | Responsible Person | Status | Comments
R1 | Gesture recognition accuracy lower than expected | High | High | High | Improve data collection and retrain model | Alice B. | In Progress | Will test with additional datasets
R2 | Backend server downtime due to high load | Medium | High | High | Scale servers and increase redundancy | Alice C. | Not Started | Will plan for extra servers
R3 | App crashes on specific iOS versions | Low | Medium | Medium | Test app on a wider range of devices | Alice D. | In Progress | Testing on more iOS versions
R4 | Delay in approval of UI/UX design | Medium | Medium | Medium | Pre-approval of designs from stakeholders | Kseniia Piskun | Completed | Approval received
R5 | Delay in hardware integration with SmartHome devices | Medium | High | High | Increase communication with hardware team | Brandon C. | Not Started | Hardware testing pending
R6 | Delay in user feedback collection | Low | Low | Low | Use email surveys for faster feedback | Claire | Ongoing | Still collecting feedback

## FMEA
Failure Mode | Potential Effect(s) | Cause(s) | Severity | Likelihood | Detection | Risk Priority Number (RPN) | Mitigation Strategy | Responsible Person | Status
FM1 | Inaccurate gesture recognition | Insufficient or noisy data | 9 | 6 | 4 | 216 | Retrain with better data, improve sensor accuracy | Alice B. | In Progress
FM2 | App crashes on certain devices | Incompatible app code | 8 | 4 | 3 | 96 | Test on more devices, fix compatibility issues | Alice D. | In Progress
FM3 | Backend service downtime | Server overload or failure | 9 | 5 | 5 | 225 | Scale infrastructure, use cloud services | Alice C. | Not Started
FM4 | SmartHome devices not integrating | API mismatch or device incompatibility | 8 | 6 | 3 | 144 | Ensure API compatibility with all devices | Brandon C. | Not Started
FM5 | Delay in UI design approval | Miscommunication or unclear requirements | 7 | 5 | 4 | 140 | Pre-approval of designs and regular feedback loops | Kseniia Piskun | Completed